## Slide 1: Training Module:
Conrad N. Hilton Foundation Substance Use Prevention Initiative
in partnership with
University of California, Los Angeles Integrated Substance Abuse Programs
SBIRT Implementation
In Juvenile Justice
Notes: TRAINER NOTES: The purpose of this training module is to provide trainees with knowledge of issues related to the implementation of SBIRT and other prevention/early intervention services related to substance use. This module was created by researchers from UCLA’s Integrated Substance Abuse Programs’ Training Center, with generous support from the Conrad N. Hilton Foundation. These materials were created for use by Conrad N. Hilton grantees as they plan and implement their substance use prevention and early intervention programs for adolescents.

## Slide 2: Training Objectives
By the end of this training, participants will be able to:
Describe the common barriers to and facilitators of SBIRT implementation
Identify two resources that can be used to help guide SBIRT implementation efforts
Identify three steps they need to take to facilitate successful SBIRT implementation in their program
Notes: TRAINER NOTES: Read the slide. Remind the audience that SBIRT is an important tool for their agency because research has shown that the majority of youth in contact with the juvenile justice system have a diagnosable substance use disorder or mental illness, and very often both.
More information on one model of SBIRT for Juvenile Justice settings can be found in the article “Implementing Screening, Brief Intervention, and Referral to Treatment (SBIRT) in Juvenile Justice Settings” at the the National Center for Mental Health and Juvenile Justice website below:
https://www.ncmhjj.com/wp-content/uploads/2016/09/SBIRT-Project-Description-011516.pdf

## Slide 3: Common Barriers and Facilitators of SBIRT Implementation
  Provider attitudes and competence
  Workflow and resources
  Student flow
  SBIRT adaptability
  Organizational support
  Client attitude
Notes: TRAINER NOTES: Read the slide. Explain that all the factors listed can either promote or inhibit the development of your SBIRT program.
Optional discussion: Looking at the list, what are the strengths/weakness of your organization?
More information about implementing SBIRT at your agency can be found in the guide, TAP 33: Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment (SBIRT) at the link below: https://store.samhsa.gov/shin/content//SMA13-4741/TAP33.pdf
This guide describes core elements of screening, brief intervention, and referral to treatment (SBIRT) programs for people living with or at risk for substance use disorders. It provides information on implementing SBIRT services and covering challenges, barriers, cost, and sustainability.
The Manual, National Center on Addiction and Substance Abuse at Columbia University: An SBIRT Implementation and Process Change Manual for Practitioners can be found at:
https://www.centeronaddiction.org/sites/default/files/files/An-SBIRT-implementation-and-process-change-manual-for-practitioners.pdf
The website, Wisconsin Safe and Healthy Schools Center: School SBIRT Implementation Project can be found at:
http://www.wishschools.org/resources/schoolsbirt.cfm
The checklist, National Council for Behavioral Health: SBIRT Implementation Checklist can be found at:
http://www.nationalcouncildocs.net/wp-content/uploads/2014/10/SBIRT-Implementation-Checklist.pdf

## Slide 4: SBIRT Implementation Manuals
SAMHSA-HRSA TAP 33: Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment http://store.samhsa.gov/product/TAP-33-Systems-Level-Implementation-of-Screening-Brief-Intervention-and-Referral-to-Treatment-SBIRT-/SMA13-4741
National Center on Addiction and Substance Abuse at Columbia University: An SBIRT Implementation and Process Change Manual for Practitioners https://www.centeronaddiction.org/sites/default/files/files/An-SBIRT-implementation-and-process-change-manual-for-practitioners.pdf
Wisconsin Safe and Healthy Schools Center: School SBIRT Implementation Project http://www.wishschools.org/resources/schoolsbirt.cfm
National Council for Behavioral Health: SBIRT Implementation Checklist http://www.nationalcouncildocs.net/wp-content/uploads/2014/10/SBIRT-Implementation-Checklist.pdf
Notes: TRAINER NOTES: These FREE evidenced-based manuals are the current gold standard in the field. They are written and compiled by preeminent experts in the field and make a good starting place for designing your SBIRT program.
The National Center for Mental Health and Juvenile Justice (NCMHJJ) is currently funded by the Conrad N. Hilton Foundation to pilot use of the SBIRT framework in juvenile justice settings to facilitate early identification and treatment of youth with or at risk for developing a substance use disorder. Using a three-phase project of planning, testing and implementation, and dissemination of findings.
SOURCE: https://www.ncmhjj.com/resources/sbirt-juvenile-justice-project-description/

## Slide 5: SBIRT Implementation Decisions
Screening
  Who do you screen?
  How do you screen them?
  Who does the screening?
Brief Intervention
  Who does the intervention?
  How brief is “brief”?
  What do you want the brief intervention to accomplish? (diversion?)
Referral to Treatment
  Who do you refer to?
  How do you follow up?
How do you implement and sustain it all?
  Data collection
  Quality improvement
  Billing
TEN STEPS TO IMPLEMENT SBIRT
Notes: TRAINER NOTES: Read the information on the slide
Optional discussion: How does your agency handle screening, intervention and referral for other issues? (For example, Depression, High BP, Vision/Hearing loss)? Can those processes already in place at your agency be used as a framework for implementing SBIRT? Why or why not?

## Slide 6: Step One: Advocate and Educate
Time and resources are essential for SBIRT to succeed
  Space
  Training
  Time to deliver service
  Integrating SBIRT into student flow and workflow
Make the case for SBIRT with administrators
  Public health
  Student health and well-being
  Emphasize potential impact on issues of concern to the school (dropouts) and how they are caused or aggravated by substance use
  What are some other ways you would make the case?
Notes: TRAINER NOTES: Make allowances for the material and logistical resources you will need to create a successful screening program. Allocate Space and time as well as give training, and booster trainings.
Involve as many staff members as possible. This shows respect for the team. The support of management and stakeholders is important to implementing SBIRT, regardless of setting. In addition, staff members are more likely to invest in SBIRT implementation if they are involved in planning from the start. In a small system (e.g., a primary care practice), it may be best to involve all staff members in the process. In a large system (e.g., a hospital system), an important first step is identifying appropriate planning participants from among service components. Who are the primary stakeholders? Who has useful skills and experience? Involving staff members from a range of disciplines and experiential backgrounds facilitates effective planning.
More information about implementing SBIRT at your agency can be found in the guide, TAP 33: Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment (SBIRT) at the link below:
https://store.samhsa.gov/shin/content//SMA13-4741/TAP33.pdf
This guide describes core elements of screening, brief intervention, and referral to treatment (SBIRT) programs for people living with or at risk for substance use disorders. It provides information on implementing SBIRT services and covering challenges, barriers, cost, and sustainability.
Citation:
Substance Abuse and Mental Health Services Administration. Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment. Technical Assistance Publication (TAP) Series 33. HHS Publication No. (SMA) 13-4741. Rockville, MD: Substance Abuse and Mental Health Services Administration, 2013.

## Slide 7: Advocacy Beyond Your Program
Identify and engage community leaders who are concerned with substance use, can help create momentum for schools to tackle the issue
  Politicians and school boards
  Community leaders
  Parents
Emphasize that this is a health approach to improving student health and wellness, not “Just Say No.”
Engage policymakers to create budgets, billing mechanisms to enhance SBIRT sustainability
  “We’ll keep getting grants” is not a good sustainability strategy
Notes: TRAINER NOTES:
More information and an overview of an effort that seeks to pilot use of the SBIRT framework in juvenile justice settings to facilitate early identification and treatment of youth with or at risk for developing a substance use disorder
can be found in the online presentation “SBIRT for Youth Learning Community: Developing an SBIRT Model for Use in Juvenile Justice Settings” by Karli Keator, MPH, the Division Director for Juvenile Justice at Policy Research Associates (PRA).
Presentation: “SBIRT for Youth Learning Community: Developing an SBIRT Model for Use in Juvenile Justice Settings”
http://my.ireta.org/node/1305

## Slide 8: Step Two Form SBIRT Teams
Identify and engage leaders from organizational units that will be involved in SBIRT
  Health staff
  Counselors
  Financial/billing
  Administration
In addition to leaders, identify potential “champions” within each unit
  Also consider adolescent representation (help make it responsive to adolescent needs/culture)
Convene regular meetings to decide on key planning and implementation questions
Notes: TRAINER NOTES: When creating SBIRT Teams-Assign clear roles and responsibilities appointing one staff member as the SBIRT coordinator may be helpful. This person can ensure that all staff members understand their roles and responsibilities and that all necessary planning tasks are completed. Develop collaborations and partnerships. Collaboration is critical, no matter the size of a system.
Citation:
Substance Abuse and Mental Health Services Administration. Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment. Technical Assistance Publication (TAP) Series 33. HHS Publication No. (SMA) 13-4741. Rockville, MD: Substance Abuse and Mental Health Services Administration, 2013.

## Slide 9: Step Three: Assess Resources and Barriers
Identify programs, staff, and procedures that can naturally be integrated into SBIRT
Develop workflow and client flow plans that reflect how things actually function in your program
Identify barriers and roadblocks that need to be addressed for SBIRT to be implemented
Develop action plans and delegate responsibilities to mobilize resources and work around barriers
Notes: TRAINER NOTES: Read the slide.
More information on reducing barriers to treatment can be found at the Network for the Improvement of Addiction Treatment (NIATx) website below:
https://niatx.net/Home/Home.aspx
NIATx is an easy to use model of process improvement designed specifically for behavioral health
NIATx offers an assortment of tools called the Process Improvement Toolbox designed to help you successfully implement change at the link below:
https://niatx.net/Content/ContentPage.aspx?PNID=2&NID=18

## Slide 10: Assessing Resources and Barriers: Let’s Try It!
Partner with colleague from your program
List resources
Identify barriers
Develop an initial action plan
How did it go?

## Slide 11: Step Four: Build Your SBIRT Protocols
Based on results from Step 3, develop a SBIRT protocol that is a good fit for your program and the adolescents you serve
  Screening tools and procedures
  Tailor brief intervention approaches
  Draft initial plans for effective referrals to treatment; begin networking with potential community partners
  Create plans for collecting data on SBIRT services delivered
  Create processes to facilitate billing and completion of administrative duties
Review protocols with entire SBIRT team, modify to address team’s concerns. Have team sign off on plan to assure consensus
Notes: TRAINER NOTES:
More information about implementing SBIRT at your agency can be found in the guide, TAP 33: Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment (SBIRT) at the link below: https://store.samhsa.gov/shin/content//SMA13-4741/TAP33.pdf
This guide describes core elements of screening, brief intervention, and referral to treatment (SBIRT) programs for people living with or at risk for substance use disorders. It provides information on implementing SBIRT services and covering challenges, barriers, cost, and sustainability.
Citation:
Substance Abuse and Mental Health Services Administration. Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment. Technical Assistance Publication (TAP) Series 33. HHS Publication No. (SMA) 13-4741. Rockville, MD: Substance Abuse and Mental Health Services Administration, 2013.

## Slide 12: Client Flow
Police or School Bring Charges
Truancy
Diversion
Programs
Traditional Tract
?????
????
????
????
????
????
????
????
????
????
????
????
S
BI
RT
Notes: TRAINER NOTES: To illustrate that there are many points of entry, we need to see where each step fits within the current client-flow through the system. Where does it make sense to place:
Screenings
Brief Interventions
Referrals to Treatment
More information on Adolescent SBIRT in the Juvenile Justice setting can be found at the National Center for Mental Health and Juvenile Justice link below:
https://www.ncmhjj.com/projects/sbirt-in-jj/
The National Center for Mental Health and Juvenile Justice (NCMHJJ) provides a national focal point aimed at improving policy and practice for youth with mental, substance use and trauma-related conditions—referred to as behavioral health conditions—who have come into contact with the juvenile justice system.

## Slide 13: Work Flow
Police or School Bring Charges
Truancy
Diversion
Programs
Traditional Tract
?????
????
????
????
????
????
????
????
????
????
????
????
Where do you have staff with:
Time?
Skill set?
Temperament?
Trainability?
Interest?
Connections with other relevant resources?
Notes: TRAINER NOTES: Read the slide. Adolescent substance use and addiction is a key contributing factor to many negative health, social, and behavioral outcomes which can cause truancy and encounters with the police. These events are the first point of engagement in the Juvenile Justice system. Wherever you have the resources and capacity in this pipeline are the good places to start implementing SBIRT.
More information on substance use and the juvenile justice system can be found at the Substance Use section of the National Center for Mental Health and Justice website below:
https://www.ncmhjj.com/topics/substance-use/

## Slide 14: Step Five: Develop Procedures and Tools to Track and Analyze Data
Define measurements critical to evaluating student success, organizational success
Define frequency, source, methodologies for collecting data
Develop databases, software, or tools to track and analyze data
Develop protocols for continually monitoring procedures, outcomes, and costs
Notes: TRAINER NOTES: Explain that patient-level information essential to effective patient care and program evaluation includes:
• Initial screening scores.
• Interventions undertaken.
• Progress notes.
• Referrals made.
• Follow-up screening scores/outcomes and treatment utilization.
• Physical and mental health symptoms or diagnoses.
• Next scheduled screening.
Evaluation is critical to SBIRT sustainability. Process and outcome evaluations can guide change, encourage staff members, and provide justification to funders.
Citation:
Substance Abuse and Mental Health Services Administration. Systems-Level Implementation of Screening, Brief Intervention, and Referral to Treatment. Technical Assistance Publication (TAP) Series 33. HHS Publication No. (SMA) 13-4741. Rockville, MD: Substance Abuse and Mental Health Services Administration, 2013.

## Slide 15: Sample Data Tracking Sheet
A mix of clinical and administrative indicators
Adolescent Name | Date Of Screen | Days Use in Past 30 Days: Baseline | Date of First BI Session | Days Use in Past 30 Days: 30 Day F/U | Referral Needed | Referral Made | Engaged in Trx
Smith, Joe | 09/09/16 | 22 | 09/13/16 | 12 | Y | 10/10/16 | 12/19/16
Notes: TRAINER NOTES: This is an example of a basic spreadsheet used for tracking SBIRT data. It shows a mix of clinical and administrative indicators. Chances are that your agency will benefit from tracking these and additional data.
These tracking sheets work best when assigned to a person who is the “Data Specialist” on the SBIRT Team. Time needs to be scheduled daily/weekly for the Data Specialist to ensure these sheets are complete and accurate.
Evaluation is critical to SBIRT sustainability. Process and outcome evaluations can guide change, encourage staff members, and provide justification to funders. SBIRT program personnel should begin to research evaluation strategies early in the SBIRT implementation process, including considering possible State, regional, and local partners, such as universities.
The following organizations or associations provide information about evaluation:
• American Evaluation Association
• Centers for Disease Control and Prevention
• Innovation Network
• Network for the Improvement of Addiction Treatment (NIATx)
More information on data collection and reporting can be found in the “Process Improvement Toolbox- How to Collect Data” at the NIATx website below.
https://niatx.net/Content/ContentPage.aspx?NID=151

## Slide 16: Step Six: Communicate With the Rest of the Program
Educate general staff about SBIRT and plans for SBIRT implementation
Elicit feedback on the contact, structure of planned SBIRT program
  Find ways to get student feedback as well
Address staff concerns and misconceptions about SBIRT and its implementation
Adjust protocols and implementation plans based on feedback from the broader program community
Notes: TRAINER NOTES: Many teams and many change initiatives falter and fall behind schedule due to ambiguous and inefficient channels of communication. Clear and direct lines of communication—whether verbal or written, electronic or manual—are essential to success.
More information can be found at the NIATx website. Many teams and many change initiatives falter and fall behind schedule due to ambiguous and inefficient channels of communication. Clear and direct lines of communication—whether verbal or written, electronic or manual—are essential to success.
Source: NIATx Process Improvement Toolbox > Essential Team Behaviors
https://niatx.net/Content/ContentPage.aspx?NID=158

## Slide 17: Step Seven: Develop Tools and Instruments to Support Implementation
Finalize and document workflows and responsibilities
Create guides and prompts to help providers interpret screens (laminated scoring sheets)
Develop scripts and tools to help providers offer appropriate responses to common scenarios
Create or purchase youth education tools (standard drink charts)
Develop promotional materials that encourage youth cooperation with SBIRT (posters, peer-to-peer communication)
Notes: TRAINER NOTES: Read the slide. Many samples of these tools and instruments can be found on the Hilton Resource Hub Website:
www.adolescentsubstanceuse.org
Evidenced based screeners and scoring sheets can be found at the Boston Children’s Hospital website:
www.teensubstancescreening.org.
Pamphlets, information and other resources oriented toward youth can be found at the National Institute on Drug Abuse website for teens:
https://teens.drugabuse.gov/

## Slide 18: Step Eight Training
Develop a customized training for all staff impacted by SBIRT
Conduct SBIRT training
Develop training schedules and procedures for new employees
Notes: TRAINER NOTES: Read the slide.
More information and training can be found at the Institute on Research Education & Training in the Addictions (IRETA) website:
http://ireta.org/online-training/
More information and training materials can be found at the Hilton Foundation’s SBIRT Resource Hub website https://www.adolescentsubstanceuse.org

## Slide 19: Step Nine: Implement SBIRT
Screenings
Brief Interventions
Referrals to Treatment
Documentation
Regular Debriefings and Troubleshooting
Notes: TRAINER NOTES:
More information on one model of SBIRT for Juvenile Justice settings can be found in the article “Implementing Screening, Brief Intervention, and Referral to Treatment (SBIRT) in Juvenile Justice Settings” at the National Center for Mental Health and Juvenile Justice website below:
https://www.ncmhjj.com/wp-content/uploads/2016/09/SBIRT-Project-Description-011516.pdf

## Slide 20: Step 10: Continuous Quality Improvement
Analyze data to find areas for potential improvement
  Numbers of encounters
  Screening scores
  Interventions received
  Referral success rate
Internally discuss ways to facilitate improvement
Look for ideas that worked elsewhere in the program or elsewhere in the SUD field, and adapt them

## Slide 21: Plan-Do-Study-Act
Example: Only 13% of students identified as needing brief interventions receive them.
PDSA
Plan
Do
Study
Act
4/5 of students no-show for their BI appointments
Create an automated system to send text message reminders the day before BI appointments
Data show that after six months, 4/5 of 12th graders are showing up for BI appointments, but only 1/5 of 8th graders are showing up
Make text message reminders standard practice for 12th graders; create group to study 8th grade no-shows
Start over, but now focus just on no-shows among 8th graders
Notes: TRAINER NOTES: Practice this slide with the animations.
More information on the “Plan-Do-Study-Act” model can be found at the NIATx website below:
https://niatx.net/PI101/PDSA/Index.htm

## Slide 22
Take-Away Points
There are many moving parts to SBIRT implementation that require planning and forethought
Goal of implementation should be not just to implement SBIRT, but do so in a way that it:
  Improves adolescent health
  Is sustainable
3. Data is critical
  Making the case for SBIRT
  Facilitating quality improvement through PDSA cycles

## Slide 23
Questions? Comments?